Implementation Plan

The implementation plan is structured into 4 phases

Phase 0:

Before any policy change goes live, lock in where effort is concentrated and establish the baseline numbers every later phase will be measured against. (Weeks 1-2)

- Prioritise City Hotel in the rollout sequence for every action below — it carries the largest share of lost revenue (Rs. 1.09 Cr, 66% of total loss) so fixes here return value fastest.

- Freeze current baseline metrics (overall cancellation rate, revenue lost, rate by hotel/segment) so every later phase can be measured against a fixed “before” picture.

Phase 1:

Quick Wins - Low Effort, Immediate Effect (Weeks 2-4)

- Charge the guest's card at time of booking, not at check-in, so a “Non-Refundable” rate actually carries a financial consequence.

- Auto-flag any booking where previous_cancellations > 0 at the point of booking; require prepayment or a mandatory confirmation call before the reservation is finalised.

- Introduce small loyalty/incentive nudges at booking (e.g., free breakfast for confirming) to increase guest commitment — cheaper than losing the room outright, and improves repeat-booking odds

Phase 2:

Segment-Specific Fixes (Month 2)

- Introduce a tiered deposit for Group bookings (e.g., 20% for 5+ rooms, scaling up for larger blocks) plus a mandatory reconfirmation 14-21 days before arrival, since organisers often lose track of headcount changes. Frame reconfirmation as a value-add (“confirm to unlock late checkout”) rather than a warning, so genuine guests are not alarmed.

- Treat “City Hotel + TA/TO + Transient” as one combined risk profile rather than three separate issues, and apply the tightened terms below specifically to this overlapping population first.

- Negotiate stricter cancellation terms with high-volume OTA partners, and reduce the default visibility of “free cancellation” rate plans on channels StayWell controls directly.

Phase 3:

Systemic Rollout - Structural and Longer-Term (Month 3+)

- Build a real-time cancellation-risk score at the point of booking, combining deposit_type, market_segment, previous_cancellations, and booking_changes. Even a simple rules-based flag lets front-desk/revenue teams prioritise which bookings need a confirmation call, instead of treating every booking the same.

- Introduce a dynamic overbooking buffer, calibrated per hotel and segment — a higher buffer for City Hotel + TA/TO + Groups, a lower buffer for Corporate/Resort — to recover some of the revenue currently lost to empty-room cancellations.

- Launch a sales push to move Transient bookings toward corporate-style commitment (deposits, contracts). Corporate-linked bookings currently cancel at only 17.5-18.6%, versus about 38-41% for everyone else — the goal is to shift enough volume that blended cancellation rates trend toward 18-20%.

What to expect:

Growth expected after Q1:

- Non-Refund deposit cancellation rate falls from 99.4% toward 50% or lower.

- Repeat-canceller bookings are pre-screened at 100% coverage before check-in.

- Group booking cancellation rate falls from 61.1%, with reconfirmation response above 70%.

- City Hotel's share of total revenue lost declines from its current 66%.

- A working cancellation-risk score is live and used by Front Office for at least high-risk bookings.

- Corporate-linked booking volume is growing quarter over quarter as a share of total bookings

Team Targets:

Revenue Management - Deposit policy enforcement, risk scoring, overbooking buffer, City Hotel prioritisation, baseline tracking

Front Office - Confirmation calls for flagged bookings, Group reconfirmation outreach

IT / Digital - At-booking card charging, risk-score implementation in the booking engine

Marketing - Loyalty/incentive nudges, pre-arrival re-confirmation messaging

Distribution / Revenue Mgmt. - OTA partner negotiations, rate-plan visibility changes

Sales / Corporate Accounts - Corporate rate agreement growth, Transient-to-corporate conversion push

Overall Outcome:

This plan sequences fixes by ease of execution and revenue impact. City Hotel is prioritised throughout, since it accounts for the largest share (Rs. 1.09 Cr, 66%) of total revenue lost to cancellations. Each phase lists the specific action, which finding it addresses, who owns it, and how success will be measured